## Thanesh Work
S.No | Assigned Task | 23 April 2024 | 24 April 2024 | 25 April 2024 | 26 April 2024 | 27 April 2024 | 28 April 2024 | 29 April 2024 | 30 April 2024 | April 2024 | 01 May 2024 | 02 May 2024 | 03 May 2024 | 04 May 2024 | 05 May 2024 | 06 May 2024 | 07 May 2024 | 08 May 2024 | 09 May 2024 | 10 May 2024 | 11 May 2024 | 12 May 2024 | 13 May 2024 | 14 May 2024 | 15 May 2024 | 16 May 2024 | 17 May 2024 | 18 May 2024 | 19 May 2024 | 20 May 2024 | 21 May 2024 | 22 May 2024 | 23 May 2024 | 24 May 2024 | 25 May 2024 | 26 May 2024 | 27 May 2024 | 28 May 2024 | 29 May 2024 | 30 May 2024 | 31 May 2024 | May 2024 | 01 June 2024 | 02 June 2024 | 03 June 2024 | 04 June 2024 | 05 June 2024 | 06 June 2024 | 07 June 2024 | 08 June 2024 | 09 June 2024 | 10 June 2024 | 11 June 2024 | 12 June 2024 | 13 June 2024 | 14 June 2024 | 15 June 2024 | 16 June 2024 | 17 June 2024 | 18 June 2024 | 19 June 2024 | 20 June 2024 | 21 June 2024 | 22 June 2024 | 23 June 2024 | 24 June 2024 | 25 June 2024 | 26 June 2024 | 27 June 2024 | 28 June 2024 | 29 June 2024 | 30 June 2024 | June 2024 | 01 July 2024 | 02 July 2024 | 03 July 2024 | 04 July 2024 | 05 July 2024 | 06 July 2024 | 07 July 2024 | 08 July 2024 | 09 July 2024 | 10 July 2024 | 11 July 2024 | 12 July 2024 | 13 July 2024 | 14 July 2024 | 15 July 2024 | 16 July 2024 | 17 July 2024 | 18 July 2024 | 19 July 2024 | 20 July 2024 | 21 July 2024 | 22 July 2024 | 23 July 2024 | 24 July 2024 | 25 July 2024 | 26 July 2024 | 27 July 2024 | 28 July 2024 | 29 July 2024 | 30 July 2024 | 31 July 2024 | July 2024 | 01 August 2024 | 2 August 2024 | 3 August 2024 | 4 August 2024 | 5 August 2024 | 6 August 2024 | 7 August 2024 | 8 August 2024 | 9 August 2024 | 10 August 2024 | 11 August 2024 | 12 August 2024 | 13 August 2024 | 14 August 2024 | 15 August 2024 | 16 August 2024 | 17 August 2024 | 18 August 2024 | 19 August 2024 | 20 August 2024 | 21 August 2024 | 22 August 2024 | 23 August 2024 | 24 August 2024 | 25 August 2024 | 26 August 2024 | 27 August 2024 | 28 August 2024 | 29 August 2024 | 30 August 2024 | 31 August 2024 | August 2024 | 01 September 2024 | 2 September 2024 | 3 September 2024 | 4 September 2024 | 5 September 2024 | 6 September 2024 | 7 September 2024 | 8 September 2024 | 9 September 2024 | 10 September 2024 | 11 September 2024 | 12 September 2024 | 13 September 2024 | 14 September 2024 | 15 September 2024 | 16 September 2024 | 17 September 2024 | 18 September 2024 | 19 September 2024 | 20 September 2024 | 21 September 2024 | 22 September 2024 | 23 September 2024 | 24 September 2024 | 25 September 2024 | 26 September 2024 | 27 September 2024 | 28 September 2024 | 29 September 2024 | 30 September 2024 | September 2024 | 01 October 2024 | 2 October 2024 | 3 October 2024 | 4 October 2024 | 5 October 2024 | 6 October 2024 | 7 October 2024 | 8 October 2024 | 9 October 2024 | 10 October 2024 | 11 October 2024 | 12 October 2024 | 13 October 2024 | 14 October 2024 | 15 October 2024 | 16 October 2024 | 17 October 2024 | 18 October 2024 | 19 October 2024 | 20 October 2024 | 21 October 2024 | 22 October 2024 | 23 October 2024 | 24 October 2024 | 25 October 2024 | 26 October 2024 | 27 October 2024 | 28 October 2024 | 29 October 2024 | 30 October 2024 | October 2024 | 31 October 2024 | 01 November 2024 | 2 November 2024 | 3 November 2024 | 4 November 2024 | 5 November 2024 | 6 November 2024 | 7 November 2024 | 8 November 2024 | 9 November 2024 | 10 November 2024 | 11 November 2024 | 12 November 2024 | 13 November 2024 | 14 November 2024 | 15 November 2024 | 16 November 2024 | 17 November 2024 | 18 November 2024 | 19 November 2024 | 20 November 2024 | 21 November 2024 | 22 November 2024 | 23 November 2024 | 24 November 2024 | 25 November 2024 | 26 November 2024 | 27 November 2024 | 28 November 2024 | 29 November 2024 | 30 November 2024 | November 2024 | 01 December 2024 | 2 December 2024 | 3 December 2024 | 4 December 2024 | 5 December 2024 | 6 December 2024 | 7 December 2024 | 8 December 2024 | 9 December 2024 | 10 December 2024 | 11 December 2024 | 12 December 2024 | 13 December 2024 | 14 December 2024 | 15 December 2024 | 16 December 2024 | 17 December 2024 | 18 December 2024 | 19 December 2024 | 20 December 2024 | 21 December 2024 | 22 December 2024 | 23 December 2024 | 24 December 2024 | 25 December 2024 | 26 December 2024 | 27 December 2024 | 28 December 2024 | 29 December 2024 | 30 December 2024 | 31 December 2024 | December 2024 | 01 January 20252 | 2 December 2025 | 3 December 2025 | 4 December 2025 | 5 December 2025 | 6 December 2025 | 7 December 2025 | 8 December 2025 | 9 December 2025 | 10 December 2025 | 11 December 2025 | 12 December 2025 | 13 December 2025 | 14 December 2025 | 15 December 2025 | 16 December 2025 | 17 December 2025 | 18 December 2025 | 19 December 2025 | 20 December 2025 | 21 December 2025 | 22 December 2025 | 23 December 2025 | 24 December 2025 | 25 December 2025 | 26 December 2025 | 27 December 2025 | 28 December 2025 | 29 December 2025 | 30 December 2025 | 31 December 2025 | 01 January 2025
1 | Task | Attended Interview For Whole Day | 1st Day to fireflink , Learning how api is working with Encryption key | learning on Implementaion of Guider | Working on Implementaion of Guider | WeekOFF | WeekOFF | Started with implementation of FireFlink Help | Worked on NLP Categories and Sub Catergories | Worked on search functionality and sideBar design | Worked on search functionality and sideBar design | Working on Implementaion of Guider | Working on Implementaion of Guider | WeekOFF | WeekOFF | Started with fireflink migration | Working on fireflink migration with websocket | Working on fireflink migration with websocket | Working on fireflink migration with websocket | Working on fireflink migration with websocket | WeekOFF | WeekOFF | Implementing Guider on NLP Admin | Implementing Guider on NLP Admin with Cache | Received Fireflink laptop and installed required Software | Started with Perfomance Module | Checking the codes for updation | WeekOFF | WeekOFF | Created new tab Perfomance and import required element | 2nd Half Leave | Sick Leave | Working on Performance Tree set | Completed with Performance Tree set | WeekOFF | WeekOFF | Sick Leave | Worked on Controller Types | Worked on types of request and TreeSet | Worked on request Sub Types (Header,Body,Setting) | Worked on request Sub Types (Script) | Started with Implementation of Performance and Migration | WeekOFF | WeekOFF | Worked on functionality of request Sub Types | Dharshan explained about NLP admin | Hardcoded responsive FireFlink Login Page | Added prerequistic and subset | Added FAQ and When to use | WeekOFF | WeekOFF | Chandan gave task on Validation of form | Optmised NLP admin Part by rectifying minor bugs | Checking on PHP codes, to change logo for 28 websites | 5 Websites logo updated | 10 Websites logo updated | WeekOFF | WeekOFF | 15 Websites logo updated | 20 Websites logo updated | 25 Websites logo updated | all 28 Websites logo updated | tab Icon updated for 8 websites | WeekOFF | WeekOFF | V-Tiger table and column data collection | V-Tiger tables relationships with EER diagram | Checking other ways to run cmd commands on client side | Deployed all 28 websites with updated logo | Completed with the assertion part in Performance | WeekOFF | WeekOFF | Updating Logos with 28 Websites and completed assertion part in Performance | tab Icon updated for remaining all 20 Websites | Deployed all 28 websites with updated Icon | Working with Swaraj with the Frontend for IT team | Created API on Spring Boots (Basic CRUD) | Started to work on the task (Provide ACOE watermark to website) | WeekOFF | WeekOFF | ACOE watermark updated for 9 websites. ### | ACOE watermark completed for remaining 20 Websites Updated all the 29 websites in the server ### | 1. Created UI for AppServer Domain page and added card flipping functionality 2. Created UI for AppServer Website page and updated 6 websites with password copying functionalities. ### | 1.Added remaining 26 websites with new UI implementation and given password copying functionalities 2. Working on Conversion of react Build to source file ### | 1.Added One more websites to App Server Domain Page and Altered Website Front Page 2. Took KT for fireflink frontend part 3. Checking on the codes of fireflink to Alter the assertion ### | WeekOFF | WeekOFF | 1. Remove Custom Assertion in Assert 2. Added Capture Data from Response to the Assert 3. Altered overlapping components in both Default assert and Capture data from response ### | 1. Check the Wesite UI and Database to validate the required data for three websites 2. In Online Banking System's website, altered Pending-customer Page and give Approve & Delete Functionality 3. Update the Realtionship in the Excel File ### | 1. To Check the similarities between UI data and database for 4 Tekpyramid websites * Bakery Shop Management System * GYM Management System * Car Washing Management System * Beauty Parlour Management System 2. Update the Realtionship between the UI data and Database in Excel File ### | 1. Provided transistion effect for appserver website page 2.To Check the similarities between UI data and database for 2 Tekpyramid websites * Sales And Inventory System * Online Shopping Alphaware 3. Update the Realtionship between the UI data and Database in Excel File ### | 1. Installed fireflink client and checking the workflow of the codes 2. To Check the similarities between UI data and database for 2 Tekpyramid websites * Online BookShop System * Online Shopping Application 3. Update the Realtionship between the UI data and Database in Excel File ### | WeekOFF | WeekOFF | 1. Installed fireflink client codes and checking the workflow of the codes 2. To Check the similarities between UI data and database for 2 Tekpyramid websites * Online Exam management System * Supply Chain Management ### | 1. Altered forms fields in default assertion component 2. To Check the similarities between UI data and database for 3 Tekpyramid websites *Health Care Hospital System *Online Food Ordering System *Hospital Doctor Patient Management System ### | 1. To Check the similarities between UI data and database for 5 Tekpyramid websites * Simple Employee Leave Management System * HRM System * Online Couple Marriage Registration System * Online PSA Birth Certificate System * Zoo Management System ### | 1. To Check the similarities between UI data and database for 5 Tekpyramid websites * Online Tourism Management System * Online Bike Rental Management System * Bus Booking Management System * Rail Pass Management System * Car Rental Project ### | 1. Installed Fireflink desktop application software 2. Took KT from dharshan on electron Js ### | WeekOFF | WeekOFF |  |  |  |  | 1. Started the project for implementation excel 2. Installed Tailwind 3. Created functionalities *Import the Excel *Edit the Excel *Export the excel | 1. Worked on project for Audio Controller 2. Worked on Adding Multiple sheet option for excel ### | WeekOFF | WeekOFF | 1. Given tab option for the Excel 2. Explored libraries to select the cells 3. Started to Work on the Handsontable Library ### | 1. Implemented select features with merge cells and stylings 2. Rejected Hansontable due to license issue 3. Research with other React Libraries for Excel Implementation ### | 1. Started to work with React Spreadsheet 2. Given Right click implementation 3. Cell selection implementation is done for right click options ### | 1. Select cell Option is not working in React Spreadsheet, so started to work on x-data-spreadsheet 2. Implemented project with x-data-spreadsheet 3. x-data-spreadsheet supports with cell selections with all excel features but it is not supported for import and export options ### | 1. Again started to work with React Spreadsheet with Old implementations 2. Found logic for selection of cell and styling the cell 3. Applied Bold, italic features for the react spreadsheet ### | WeekOFF | WeekOFF | 1. Aplied font color and background color options for React spreadsheet 2. Removed import features and added Json formate 3. Implemented excel sheet according to the json formate ### | 1. Implemented the styling features by changing the json object 2. worked on bold, italic and given border features with its types in react spreadsheet 3. Implemented the styling features according to the json object ### | 1. worked on bold, italic and given border features with its types 2. Tried to create Reusable component for Color , border Color and background color 3. Went GC to receive marksheets 3hrs ### | WeekOFF | 1. Created reusable components for Dropdown and import color 2. Implementation of reusable components for dropdown and color bar is successfully completed ### | WeekOFF | WeekOFF | 1. Implemented additional features like text align , formate Painter , undo and redo 2. Implemented excel project in fireflink application where add column and add row is not working | 1. Implemented add column and add row features again with delete functionalities 2. Created separate section for excel with data conditions and created only for file type excel | 1. Create excel logo for the file 2. changed the size of the excel sheet as per the design |  |  | WeekOFF | WeekOFF |  | 1. Got excel Backend Jar File from dharsan 2. Installed Postman and after running the jar file which import in postman postman 3. Checking the api is working or not 4. After postman is working, Started to implement the API in excel spreadsheet | 1.Excel spreadsheet implementation with local API 2. Data is not getting properly from the backend getting Error when using get API 3. Removed undo, redo functionalities | 1. Updated the firflink UI with updated version JULY_V1 branch 2. Started to implement with the updated codes 3. Removed Border functionalities where the logic changed from UI perpective | 1. Completed with the API implementation 2. Pushed the codes and created MR 3. Resolved the the comments from the MR 4. Created New Jira account for me and got the design for Excel implementation | WeekOFF | Ongoing | WeekOFF | 1. Started to work with performance 2. Updated the latest codes with performance 3. Preparing SVG icons from the design to upload in fireflink Library 4. Send those icons to Vikas for upload it in the FF library Icons | 1. Vikas uploaded the excel icon in the ff_library but it is not yet published 2. Jitu explained the backend Codes regarding the performance 3. Changing Create test plan menu according to the standard library (replacing material UI with Firflink Component ) | 1. Informed to Viswanath regarding FF_library is not yet published 2. After the library is got published 3. Got CORS policy from the backed which is server error (Nginx issue) 2hrs | 1. Ranjith gave new design 2. Edit , save and Export converted to (Edit , Export) and (Save , Cancel) 3. Implement the functionalities for Edit , Export, Save and Cancel 4. Implemented the Warning notication for saving the file | Took WFH 1. Implemented create file option in test data sections 2. Dissussed in call with ranijith regarding proper design for warning notification 3. Attended call FF libarary new component, explained with LLD and HLD | WeekOFF | WeekOFF | 1. Mohan sir Expalined about CIBC report and gave the sample data 2. Created cards and styled according to the report 3. Basic card design implemented | 1.provided warning, notice and error tab 2. Attended Call for performance implementation 3. Mailed to provide VPN access and got installed VPN from Sumanth | 1. provided functionalities for the tab 2. created Home section and provided functionality for the home section 3. Worked to achieve nested list dropdown 4. Implemented with Json formate | 1. Dropdown is not working as expected for multiple tab 2. worked on the issue dropdown and found that we should have to provide different key for different tabs 3. Making "Standard value" as dynamic value 4. Provided functionalities to the list which sould not get render if the count is zero | 1. Created side menu option which have multiple web pages 2. provided implementation to the side menu with openeing and closing condition 3. Worked on rendering error images and count value of the list , nested list | WeekOFF | WeekOFF | 1. Started to implement excel component in FF libraray 2. R&D on Typescript 2. Took KT from sohail about basic implementation from ff library 3. Created new component and added some features | 1. Converted all the codes to typescript formate 2.Went to cafeteria to create salary account in ICICI bank 3. discussed typescript codes with sohail and learned about rendering and useCallback | 1. Created separate useState to avoid the rerending of the component 2. Did R&D on positioning the context menu 4. Sohail followed new appraoch using getBoundingClientRect() 5. Created merge request to the ff library main branch | 1. Got 32 issue from excel libraray 2. Solved 28 minor issues and 2 majour issues 3. Attended meeting in 5th floor (Explained coordination of developer and Tester) | 1. Breakdown the component to ExcelFile, sheetTab, contextMenu and colorBarSelector 2. Dynamic Alignment of context menu when It goes to the end of the page 3. Attended call for new library implementation 4. Finally Merged Excel to FF-Library | WeekOFF | WeekOFF | 1. Getting errors on using yarn build 2. Discussion with Padmakanth and Viswanath and deployed codes to Fireflink Library 3. Started with performance , created new tab section and provided valid routing for that | 1. Fireflink excel library is not working in fireflink UI 2. Tried all scenarios to run excel library , getting error ..api// from libaray 3. Discussed with viswantha koli and did trail and error to check the root cause of the error | 1. Found the source file for excel and cancelled excel library due to publish issue 2. Again strated with implementing with Fireflink ui 3.Started with Unit Testing for the manual test scenarios | 1. Discussed about the reqiuement (dharsan, sakieb ,Ranjith) 2. Solved issue - added line loader , fixed file validation, icon size 3. Unit testing for Excel validation 3. Started with perfoemance, added perfomance file to the updated codes | 1. Got 502 error preprod server down for 2hrs 2. Solving updation of useState data and avoiding infinite render 3. Given demo about the Excel implementation 4. Resolved Problems about the context click | WeekOFF | WeekOFF | Solved Test Case around 6 1. FLN -19659 2. FLN -19661 3. FLN -19664 4. FLN -19668 5. FLN -19670 6. FLN -19677 |  | 1. Sakib explained how jira is working and how to assign task and update status 2. Requirement Change is happened which is not in the design 3. Backend is more depending on frontend 4. Resolved server error 500 , where I have to send text align in Capital letter | Ganthi Janthi | 1. Understanded workflow of breadcrumb and created new breadcrumb functionalities 2. Attended Code Flow call 3. Discussed about getting empty cell data with viswanth 4. preprod is not working and particularly get file API is not working 5. Renaming Sheet without infinite redering is completed | 1. Context menu is working locally but not working in the server 2. Altered the Logic of context menu options 3. Attended Code Flow call 4. Discussed with saqeb about merging backend codes 5. Issue ticket FLN-19823 , row and column is not getting added upon saving which comes from the backend 6. once the backend is got solved, analysed what kind of empty data comes from the backend | WeekOFF | WeekOFF | Sick Leave | 1. Working on issue FLN-19858 navigate to blank page upon changing the sheet 2. On working on renaming sheet , I hardcoded some data which is not dynamic 3. Provided dynamic value on renaming and chnaging sheet 4. Worked on issue FLN-19864 which is getting 500 on opening uploaded file 5. i am getting null value for no data and for proper border style upon saving the file | 1. woking on issue FLN-19810 , border is not working and found error from the backend 2. Working on issue 401 on saving data, it is because of sending text align in small letter instead of capial letter 3. working on issue FLN-19860 data getting re-arrange on saving the data 4. solved the issue and pushed the codes 5. Ranjith came with another requirement change for max file load | 1. Working on column which should not dissapper even after saving the file 2. Ayudha pooja in our office for 1hrs 3. Tried to handle the error form the backend for max load file 4. Disscused with saqeb that the error should get handled by the backend | Ayudha Pooja | WeekOFF | WeekOFF | 1. Working on issue FLN-19975 , if adding row and column without selecting cell is not working 2. Altered new feature unsupported file and file too large 3. Created merge request before updated with latest pull | 1. Started with performance 2. Jitu asked to work on dropdown task 3. Removed unwanted codes in performance 4. Got comments in test data and solved 5. removed headers from the api and altered some codes for merge | 1. Doing WFH, statred with performance 2. Altered the tree struture to create one more parent option 3. One ticket have raised in testdata , regarding getting 500 internal error on deleting cell 4. Working on the ticket and found the issue , during code review i altered some logics which caused the error 5. created merge request and asked saqud to publish the codes (follow through) | 1. Completed with performance tree and working with the option for implemented Parent option 2. Provided proper responsive ui for controllers 3. Attend QA meeting with saqeb, abisek, dharsan 4. Discussed the problem FLN-20060 and FLN-20061 5. Checking the codes on how the Variable selection path is working ? | 1. worked on nested dropdown menu for jitu's work, For nested dropdown did R&D in bootstrap , react boostrap and material UI 2. Finally created custmised nested dropdown menu 3. Worked on the Ticket FLN-20064, chatbot is not working inside excel test data 4. Solved the problem FLN-20064 , Created merge request and closed the ticket | WeekOFF | WeekOFF | 1. Working in performance and it got stopped 2. Got issue in testdata FLN - 20064 where user not able to access chatbot 3. provided add eventer listerner for the whole sheet where it is preventdefault keypress which affect the chatbot 4. Tried with 2 to 3 apprach and alterend the add event listener only to the spreadsheet | 1. Working on the issue FLN-20112 in testdata, where the sheet is getting constrained by adding multiple sheet 2. Clarifying the requirement about the validation in the sheet name and maximum lenght of the sheet name 3. Working on the issue FLN-20120 in testdata, While pasting the column from the One page to another , navigating to blank page 4. Solved both the issue and pushed the codes and craeted mergee request | 1. Working on the issue FLN-20136 in testdata, where the sheet is getting navigated to blank page upon click Add sheet context menu 2. Installed MongoDB and import performance API to the local 3. checked create testplan and fetch testplan API is working or not 4. Got issue FLN-20138 , the styling is not working upon selecting row and column | 1. Working on the task FLN-20138, and completed 2. pushed the codes, created MR, follow through upto the publish 3. The solution is not working in the deployement server, but it is working in the local server 4. Again changed the logic by removing the construtor and targeting the element using DOM 5. Solved the issue and pushed the codes, created MR, follow through upto the publish and done unit testing | 1. Working on the issue FLN-20148, this is will rise the problem in test data where getting empty cell 2. Provided condition for style which prevent the style from getting erased 3. Discussed this regarding with saqeb and ranjith , so they planned to push this in the next phase 4. Started with performance , updated backed in my sysytem and uploaded API in post man | WeekOFF | WeekOFF | SL | 1. Working on Create Test plan API , where the data is send through form data 2. if I sent as form data as Object then it will take as reference 3. if I sent as string then it will add addtional escape sequence and giving 500 Internal error 4. Discussed with jitu to change the way he get data, instead of body use header and he said this is how the whole application working 5. Tried to Connect with viswanath and he told me to connect with Ayush Jaishwal | 1. WFH, Tried to solved the internal issue 500 2. Connected with Ayush Jaishwal and discussed about sending data to body as form data 3. If we are sending data through body as form data then we have to provide header as "formdata" 4. Completed with create test plan API and started with R & D how to get local and test data 5. Connect with Srinivas to get help to check how local variable is working |  | Diwali Holiday | Diwali Holiday | WeekOFF | WeekOFF | 1.Integrated with Create Testplan API , get all Test plan api and get individual test plan api 2. Attended performance grooming call where discussed the performance flow 3. Optimized the code structure of the tree component and removed unwanted files | 1. Jitu cahnged the logics of the test group section where I got problem in sending data 2. Jitu gave new jar file and started to work with new jar file 3. Intergrated Delete test plan api, created Test Group api and delete test Group Api | 1. Disscussed with viswanath about the performance where we can to conclusion 2. It will take lot of time where we cant complete the within 15 days 3. I got news where they planned me to put on test data section and someone else is going to take performance 4. Attended performance design grooming where they totally chnaged the frontend design | 1. worked on the issue FLN-20272, where the excel data is not coming form backend if the first row is empty 2. Started with column and row dragging functionality in excel component 3.Got new storybook and fireflink UI access from the padmakanth and installed the setup 4. Once got the Code acces tried to setup the project | Work from Home 1. Ayush tried to connect but he finnaly connected on 12:45 2. Until I tried to check with microfrontend architecture 3. Ayush connected and told that he will connect after 6 4. Gave code setup to Abdul 5. Ayush explained test data old ui section after 6 | Saturday Worked in GC 1. Continued with converting the spreadsheet library to component 2. Got Typescript error and solved all the typscript errors 3. Finally the Spreadsheet is working in the storybook component 4. Got code KT from Ayush about test data 5. Explained my approach towards the excel implemantation | WeekOFF | 1. Discussed about the feasibilty of the excel with Nitin, Saqeeb, Padmakanth 2. Dragging option and formula is theimpotant one so started to work with formula 3. Formula is working with the spreadsheet sheet 4. Tried with Dragging option | 1. Planned to check with compability of the excel sheet in storybook 2. Started to implement tool bar which requires Toolbar Icon 3. Done R&D and gave requirmenet to desing team that what are the icons needed 4. Once got the Icon , updated all 20 icons in the storybook and created MR | 1. Started to check compability by publishing the code with help of sudeep 2. Getting Typescipt Error while creating build for sudeep, but error is not occuring for me 3. Found the cause and solved the build problem 4. Css is not working and converted all the color formate from spreadsheet to firflink formate 5. Publised the storybook on my own and checked the feasiblity | 1. R&D on spreadsheet and Change workflow of toolbar in the spread sheet 2. Using seperarte toolbar is going infinte loop 3. Found the way to provide toolbar inside the library 4. Provided Functionaity Bold, Italic, Color and Background Color | 1. Started with aligning tool bar as per the design 2. Provided Excel tool bar functionality font family, font size, underline, strikethrough, double, underline,all Borders, Text Align 3. Worked with dharshan on fetching images based api for fireflink ai sphere 4. Raised MR for the tool bar functionalities | Saturday Worked in IndiQube 1. Started with implemantation of sheet bar 2. Provided styling for the sheet bar as per the design 3. Created functionality to change the sheet 4. provided renaming functionlity for the sheet with validation 5. Created add sheet functionality on clicking add icon and Raised MR | WeekOFF | 1. As Viswanath suggested did R&D on breaking reducer file 2. Created seperated function to reduce the file size of the reducer.ts 3. Converted the classnames from spreadsheet to fireflink standards 4. Component is going to infinte render and on checking issue is comin from the select menu | 1. Added corner icon to the excel sheet as per the design 2. Did R&D on provding context menu option to find the flow 3. Provided Functionalities for Add row , Add coloumn, Delete Row and Delete Column 4. Providing Icon for the right click menu that mention above but position is not working 5. Raised MR for context Menu option | 1. Got API issue which we got before while implementing Spreadsheet in library 2. Error is getting only if we created build, if we are not creating build then it is working 3. Tried with removing few functions and tried with trial and error method 4. Finally found the reason for API issue and removed the library formula Parser | 1. Worked on Add sheet and Delete sheet functionality 2. Provided context menu for add and sheet 3. Getting conflicts with header context menu and sheet menu , Solved the issue 4. R&D on Formate Painter functionality which should get applied by selecting the cell ( worked with the redux global) | 1. Implemented Formate painter functionality 2. Raised MR Add sheet and delete sheet functionalities 3. Worked on tool bar stylings as per the design due to tomorrows demo 4. Removed Row and Columns and provided dynamic styling for the tool bar 5. Added file type Icons to the storybook and created MR | Saturday Worked in IndiQube 1. R&D on positioning context menu option for row and column 2. Implemented positioning of context menu option for row and column 3. Changed sheet bar styling as per the design 4. Demo on Test data - Gave Excel demo to Jagadesh, Manya, | WeekOFF | 1. Solved minor issues got in the demo (data not changing while deleting sheet, text color link with background color) 2. Created MR for the above issues 3. R & D on Row dragging and Column Dragging functionality through redux 4. Implemented row dragging funcionality 5. Issues with style while selecting one row and dragging another row | 1. Solved the styling issue in row dragging functionality 2. Implemented column dragging functionality with proper styles 3. Resolved MR comments created by viswanath and Ayush 4. R&D on data conversion for data 5. Created new file to convert backed data to frontend data and vice versa | 1. Provided save file functionality with CRTL+S 2. Completed with tool bar variant with Bold , Italic and underline type 3. Solved issue by selection multiple cell 4. Resolved comment around 4 to 5 5. Checked with the build and solved build errors and created MR for file convserion and Row & column dragging functionalities | SL | 1. Got issues with dragging which is not able to solve 2. Started with R&D on the formula 3. Did trial and error on circular dependency 3. Created build and created MR for Variant tool bar | WeekOFF |  | WeekOFF | 1. Fixed Excel Dropdown issues in component level - connect with dhanush 2. R&D on drag and drop functionality | Functionality for drag and drop | Styling issue in drag and drop Library to ff platform | Excel Integration --> done Row fixing header | 1. 2. Worked on the row and column fixing functionality | 1. Test data section is not working due to change in tress component 2. Connect with ayush and fixed the issue by removing tree data in excel component 3. Again I got same error, so removed tree data in whole test data section 4. Tracked the flow Fixing the changes,MR and deployment 5. Gave demo for Excel compoent to Viswanath and save the comments | WeekOFF | 1. Started with R&D to fix row and column hider 2. Tried with providing direct styling apprach which is not working due to seperate component 3. Solved the issue where user cannot Enter Data on Single click on view mode 4. Gave demo to product team along with saqeb and ayush 5. Got many new feature implementation like border thickeness, select all should not navigate, Design for sheet bar | 1. Started with R&D to fix row and column hider 2. Solved row and column hider by providing seperate empty div 3. created MR for row and column hider fix and solved comments 4. did R&D on drag component to find the root cause of the issue 5. Finally found a apprach to solve drag and drop issue | 1. Working on other ways to solve drag issue 2. Implemented 2 to 3 ways to solve the drag isuue which invoking other issues 3. Disussed with viswantnth and Ranjith about the implementation 4. Finally fixed to the latest implemantation which cause select issues 5. Solved styling issue when we go to Edit mode | 1. Worked on context menu positioning 2. Worked for ACOE in implementing old fireflink UI with extra menu feature in webservice 3. did few trial and error on publishing library multiple times 4. Finally come up with optional prop for positioning context menu 5. provided extra prop (onCollapse) tp drawer compoenent 6. Created MR for context menu positioning in libaray side | 1. Created MR for Context menu positioning from platform side 2. Worked for ACOE in implementing API to upload collection file 3. Got CORS error which srinivas solved 4. Provided Save functionality design to the platform side and created MR for save functionality | 1. Reviwed MR comments 2. Gave Demo for Excel component 3. R&D on delete and backspace | WeekOFF | 1. Started with Intergration of Get excel API 2. Server preprodonprem is not working with saqeb credentials 3. Ayush gave KT on how mutation and Query works in RTK 4. Got Issue in backend data, Excel component is not rendering 5. After checking get to know that backend passing 'styles' instead of 'style' | 1. Raised MR for Libarary and Platform for updated font type and get Excel Api intergration 2. Discussed with product team about the font type and font size 3. Finalised the font types and font size and updated with jira comment 4. R&D on backspace and delete functionality 5. implemented backspace and delete functionality | 1. Started with providing props to hide toolbar and sheet bar 2. Added rowCount and ColCount props 3. Provided KT to sujith and provided additional contex menu option and creted MR for the props and menu 4. Started with 500 internal server issue 5. Working on the internal server issue 6. Completed with postman Collection task by ACOE | 1. Found the Internal Error issue is due to background color passing as Variable 2. Discussed with padmakanth and viswanath about the issue and told to change in backend 3. Discussed with Darsan about the issue and he told we cannot change in apache poi 4. Again had disscussion with saqeub and viswanath and concluded with we are not providing Theme for Excel 5. Changed the background color and color with hexacode and created MR and got merged | 1. Completed with save Excel file API intergration and working fine in staging 2. Tried to intergrated in dev2 env 3. Got 2 dependencies, one is Tree integration is not done, so create project and file thorugh postman and second after creating project got 500 internal issue because S3 bucket is not assigned 4. connect with saqeb and tried to resolve those internal error 5 . Discussed about MTC backend and frontend requirement with Koushik and saqeb | 1. Getting CORS error in dev2 env and connected with staging env 2. Getting CORS error in staging env also 3. Tried to connect with preprod , not worked so not able to give demo for excel integration 4. R&D on copy paste both style and value from one platform to another platform | WeekOFF | 1. R&D on multiple input from excel 2. Created basic flow structure for the input types 3. Resolved 500 internal issue (file is null) due to missing file name 4. still CORS is not resolved and connect with dharshan for toStirng error while creating new file 5. Discussed about the input types that we will send to backend with Koushik and dharshan | 1. Sujit got error while adding row and column 2.Resolved the issue and raised MR for that issue 3. Added input type props structure and implementaion 4. Discussed about the upload files properties and conditions with viswanath and Ranjith 5. Conditional rendering for input type according to row , column and cell | Christmas Holiday | 1. R&D on how to add attachments and dropdown in Excel 2. Got issue in Active Cell,data Editor and Cell,Data Viewer which both are different component 3. Did R&D and Came up with one apprach by providing conditional active cells 4. Got functionality issue , getting two value *from Data Viewrer *from Active Cell 5. Solving the above issue, by providing condition for data viewer as well | 1. Solved the issue data will not visible in view state for input file and dropdown 2. Fixing the Alignment issue for the input type 3. Gave demo to ranjith and saqeb on the dropdown and file attachment in excel 4. Got issue with the API then get to know it was endpoint issue 5. Connected with Padmakanth and sheeraz and solved CORS error 6. Raised MR for issues fixed for input type dropdown and attachment in excel | WeekOFF | WeekOFF | Sick Leave | Sick Leave |  | New Year | 1. Solved sheetbar related issue, typography is not applying on renaming the sheet, flickering issue on double click 2. Naming sheets according to the requirement newSheet --> sheet1 3. provided variants for font family and font size 4. Discussed with viswanth about the input feilds and gave suggestion for dropdown to provide options on selecting the cell 5. Added new prop for the select for option to open on condition 6. Create excel file issue is resolved , but getting 404 error on save api | 1. Found issue while changing the screen and removed Selection type on changing the sheet 2. Connected with Koushik regarding 404 Error and found the error is due to changes in endpoint 3. The endpoint the changing from one development server to production 4. Raised MR for the API endpoint change but viswanath not approved the change 5. Connect with saqeb to change the endpoint from backend side instead he convinced viswanath to merge the MR | WeekOFF | WeekOFF | 1. Everyone got issue for Select component , option is getting opned at start 2. Resolved the issue of select options and raised MR for the issue 3. Disscussed about dependeny type of issues with saqeb 4. Disscussed with ranjith regarding the below issue and resolvedfew of them 5. On creating file got 500 Internal issue (due to extra tree ) and it got solved by Koushik and it took time due to dependency with tree | 1. Sujith came with excel issue , deleting extra column , cell is not getting etidable while adding 2. On checking copy, paste and adding column row does not copyiny the input types 3.Worked on the above issue and raised MR for the issue 4. Discussed with Product team Ranjith about the 1000 row validation and concluded with the validation 5. Commented on jira regarding the validation and new feature implementation 6. Got 500 internal issue and discussed with Kushik and he told it was tree issue so again connected with Punith | 1. Sujith came up with issue by adding readOnly in background is not working 2. Worked on the issue and raised MR after solving the issue 3. discuusion about Input file attachement where we can store all the files that can upload in S3 3. Added props to the input component for the excel 4. Resolved Style issues in the sheet bar 5. R & D on blocking styles for read Only Cell 6. Implemented blocking of styles for readonly cells and discussed about the consequences that it will not work for cut, copy paste |  |  | WeekOFF | WeekOFF | [5 empty] | WeekOFF | WeekOFF | [5 empty] | WeekOFF | WeekOFF
2 | Additional Task | [29 empty] | 2nd Half Leave | Sick Leave | Approach 1 | Approach 2 |  |  | Sick Leave | [7 empty] | Checking on Assertion Codes for Request subType | Started to work on NLP admin |  |  | Checking on Assertion Codes |  |  | Checking on Assertion Codes | [10 empty] | Mohan explained about V-Tiger requirement | [5 empty] | Working On socket io to run cmd commands on client side | [80 empty] | Issues 1. Handling large amount of data in CIBC 2. huge Json object is not working while we deployed |  |  | Learned About the Typescript interface | There is a limit to use useCallbak or else it will go infinite rendering | R&D Right Click Event pageX,pageY clientX,clientY screenX,screenY scrollX,scrollY sheetRef.current.getBoundingClientRect() | 1. Created separate useState to avoid the rerending of the component 2 . Managing the states which uses two scenarioes |  |  |  | Publish Flow : - yarn yarn build yarn publish | Problem 1.codes are correct 2. build succsesfully 3. build published successfully 4. excel component is working well in storybook 5. but getting ..api error while using the component | Work Flow 1. Work according to the design 2. Parallelly check with the jira to have complete understanding of the requirement 3. Consult with senior developer and team to have better clarification 4. once the development is completed deploy in the pre production 5. write Test scenarios for those test cases as per the requirement given the jira 6.DO unit testing for those test cases using pre production 7. Test enginner raise tickets or bugs for the issues 8. Solve the issue according to the priority | Issue 1. Laptop is very slow , so switching the project is very difficult 2. Parallely maintain to task is much more challenging but , I have to pay time as a price | Demo Call 1. Given excel implementation demo for test engineers and PD team Issues 1. Preprod Server is down for 2hrs | WeekOFF | WeekOFF | When test case are created first priority goes to P0,P1 They are important because they are blocker type of test cases |  | Issue Specify want data you need to validate in the frontend and backend | Ganthi Janthi | Issues No environment to run frontend ( 3hrs ) | Workflow 1. If you have any requirement clarification change the status 2. if the requirement is provided orally then don’t accept ask for detailed information | WeekOFF | WeekOFF | Sick Leave |  | Issue 1. when we save file , added column is not getting added 2. the null value is accepted as empty | requirement Change 1. Wanted to add new page for viewing max load Data 2. For max load im getting respond 412 instead of 200 , and informed to dharshan | Ayudha Pooja | WeekOFF | WeekOFF |  | Issue 1. Came late to office 10:05 because of rain | Ethics 1. If you are working in project make sure the project is done orelse follow up the project |  |  | WeekOFF | WeekOFF | Process Flow for Solving Ticket 1. Once Ticket raised in jira , update the staus to Dev-in-progress 1. Solve the issue in the code 2. Push the code 3. Create Merge Request 4. Review the Code 5. Resolve the comments from the code review 6. After solving the comment merge the branch 7. Publish the branch 8. Do unit Testing 9. Close the Ticket 10 .Update the status to dev-completed | Issue 1. One funtion calling two time, one from "Icon" useState is working and another from "Button" useState is not working 2. The issue is the function is getting invoked from the switch case, the useState is not getting updated 3. But function is getting invoked from the button event, the useState is not getting updated Solved 1. Mohan sir solved the issue , it is because of calling switch statement inside the usestate which does not return any statment | Issue So many requirement changes are happening due to improper design | Issue 1. After solving the issue it is workin in locally but not working in server 2. After changing the Logic ,replaced Constructor with another logic Note Don’t use Constructor name in react | Ethics 1. Check for the test case where one feature will work but it will make error in other feature 2. Make wide mind to check for those errors 3. Once the Requuirement is got freezed, you cant create MR to the main branch | WeekOFF | WeekOFF | SL | Learned how to send form data from body |  |  | Diwali Holiday | Diwali Holiday | WeekOFF | WeekOFF | [6 empty] | WeekOFF | Issue 1. Dragging option takes usally more time than I though 2. Daily we have morning Standup meeting | Process Flow 1. Learaned How to publish the npm package 2. Create account in npm 3. yarn 4.yarn build 5.npm login 6.npm publish | Issue 1. im not encountering typscript issue during build because I changed Type value in the node modules which is not a proper way 2. While restarting the package it will get change | Process 1. Understood deep understanding of spreadsheet comp and Reducer , Action and Dispatch method where handling the Global store |  |  | WeekOFF | R&D 1. We cannot break the reducer as it hold only one Global store 2. By creating Two file by having One global store is not the proper flow 3. We can have Multiple reducer if we have multiple global Store |  | Issue 1. Encountered API issue 2. Component in storybook will work even if we use build , if we try to use in as storybook library then also it will work 3.i f we try to use in as storybook library and created build then we will get API issue 4. API issue is coming when we are using some Old dependencies that is not supported by Babel |  |  |  | WeekOFF |  |  |  | SL | Need Cicular Dependency for Formula | WeekOFF |  | WeekOFF | [6 empty] | WeekOFF |  |  |  |  | Learning CORS error will rise due to strict access for port from backend side we can provide access as * to provide access to all the ports |  | WeekOFF | Learning 1. In RTK query, they are two thing mutation and Query 2. Mutation works with post and put 3. Query Helps with Get method | [5 empty] | WeekOFF |  |  | Christmas Holiday |  | Learning 1. For Css , getting default height for display: flex; property 2. If header is adding in backend then changes must be reflect in frontend and devops (Engine x) | WeekOFF | WeekOFF | Sick Leave | Sick Leave |  | New Year |  |  | WeekOFF | WeekOFF | issue Product Team 1. Test data upload file - same file - validation from frontend 2. On import scenario File validation 3. MTC basics design template for editable and non editable headers 4. What will Happen if we freeze header - Style will apply or not Backend Dependecny 1. Getitng 500 Internal Issue - Resolved need to pass fileType:xlsx 2. MTC API with Excel 3. How the File Attachment is working with Common API 4. API for import Excel sheet |  |  |  |  | WeekOFF | WeekOFF | [5 empty] | WeekOFF | WeekOFF | [5 empty] | WeekOFF | WeekOFF

## Logo_Icon_Web
1
2

## Performance
1 | Added Performance Tab
2 | Splited the perfomance , right and left and worked on performance tab opening and closing
2 | Default right side or Quickstart setup
3 | Created a component to create new test plan or new test Group
4 | Worked on Performance Side Bar Tree
5 | Worked on Controller Types
6 | Worked on request Types and Tree Set
7 | Worked on request sub-types
8 | Worked on request sub-types (Script)
8 | Worked on request sub-types (Script)

## Realationship_Tables
S.no | App Name | DB_Name | Module Name | Table(Column_Name) | TableDetails | UI Mandatory Fields=>db name
1 | V-Tiger | vtigercrm540 | Leads | vtiger_leaddetails ( leadid, lead_no, email, interest, firstname, salutation, lastname, company, annualrevenue, industry, campaign, rating, leadstatus, leadsource, converted, designation, licencekeystatus, space, comments, priority, demorequest, partnercontact, productversion, product, maildate, nextstepdate, fundingsituation, purpose, evaluationstatus, transferdate, revenuetype, noofemployees, secondaryemail, assignleadchk ) | pri_key --> leadid, mand --> leadid, lead_no, accountid, company, lastname, | Last Name=>lastname, Company=>company,
|  |  |  | vtiger_crmentity (crmid, smcreatorid, smownerid, modifiedby, setype, description, createdtime, modifiedtime, viewedtime, status, version, presence, deleted) | pri_key --> crmid mand --> crmid, smcreatorid, smownerid, modifiedby, setype, createdtime, modifiedtime, version, deleted | -
|  |  | Contacts | vtiger_contactdetails ( contactid, contact_no, accountid, salutation, firstname, lastname, email, phone, mobile, title, department, fax, reportsto, training, usertype, contacttype, otheremail, secondaryemail, donotcall, emailoptout, imagename, reference, notify_owner ) | pri_key --> contactid mand --> contactid, contact_no, lastname | Last Name=>lastname
|  |  |  | vtiger_crmentity (crmid, smcreatorid, smownerid, modifiedby, setype, description, createdtime, modifiedtime, viewedtime, status, version, presence, deleted) | pri_key --> crmid mand --> crmid, smcreatorid, smownerid, modifiedby, setype, createdtime, modifiedtime, version, deleted | -
|  |  | Organizations | vtiger_account ( accountid, account_no, accountname, parentid, account_type, industry, annualrevenue, rating, ownership, siccode, tickersymbol, phone, otherphone, email1, email2, website, fax, employees, emailoptout, notify_owner ) | pri_key --> accountid mand --> accountid, account_no, accountname | Organization Name=>accountname
|  |  |  | vtiger_crmentity (crmid, smcreatorid, smownerid, modifiedby, setype, description, createdtime, modifiedtime, viewedtime, status, version, presence, deleted) | pri_key --> crmid mand --> crmid, smcreatorid, smownerid, modifiedby, setype, createdtime, modifiedtime, version, deleted | -
|  |  | Documents | vtiger_notes (notesid, note_no, title, filename, notecontent, folderid, filetype, filelocationtype, filedownloadcount, filestatus, filesize, fileversion) | pri_key --> notesid mand --> notesid, note_no, title,folderid,filesize | Title=>title
|  |  |  | vtiger_crmentity (crmid, smcreatorid, smownerid, modifiedby, setype, description, createdtime, modifiedtime, viewedtime, status, version, presence, deleted) | pri_key --> crmid mand --> crmid, smcreatorid, smownerid, modifiedby, setype, createdtime, modifiedtime, version, deleted | -
|  |  | Oppourtunities | vtiger_potential (potentialid, potential_no, related_to, potentialname, amount, currency, closingdate, typeofrevenue, nextstep, private, probability, campaignid, sales_stage, potentialtype, leadsource, productid, productversion, quotationref, partnercontact, remarks, runtimefee, followupdate, evaluationstatus, description, forecastcategory, outcomeanalysis) | pri_key --> potentialid mand --> potentialid, potential_no, potentialname | OpportunityName=>potentialname, Realted To=>related_to, Sales Stage=>sales_stage
|  |  |  | vtiger_crmentity (crmid, smcreatorid, smownerid, modifiedby, setype, description, createdtime, modifiedtime, viewedtime, status, version, presence, deleted) | pri_key --> crmid mand --> crmid, smcreatorid, smownerid, modifiedby, setype, createdtime, modifiedtime, version, deleted | -
|  |  | Products | vtiger_products (productid, product_no, productname, productcode, productcategory, manufacturer, qty_per_unit, unit_price, weight, pack_size, sales_start_date, sales_end_date, start_date, expiry_date, cost_factor, commissionrate, commissionmethod, discontinued, usageunit, reorderlevel, website, taxclass, mfr_part_no, vendor_part_no, serialno, qtyinstock, productsheet, qtyindemand, glacct, vendor_id, imagename, currency_id) | pri_key --> productid mand -->productid, product_no, productname,discontinued,currency_id | Product Name=>product_name
|  |  |  | vtiger_crmentity (crmid, smcreatorid, smownerid, modifiedby, setype, description, createdtime, modifiedtime, viewedtime, status, version, presence, deleted) | pri_key --> crmid mand --> crmid, smcreatorid, smownerid, modifiedby, setype, createdtime, modifiedtime, version, deleted | -
|  |  | Campaign | vtiger_campaign (campaign_no, campaignname, campaigntype, campaignstatus, expectedrevenue, budgetcost, actualcost, expectedresponse, numsent, product_id, sponsor, targetaudience, targetsize, expectedresponsecount, expectedsalescount, expectedroi, actualresponsecount, actualsalescount, actualroi, campaignid, closingdate) | pri_key --> campaignid mand --> campaignid, campaign_no | Campaign Name=>campaignname